## Title
| Form F-ITOP-008 Deployment Plan |  | Revision Number: 01
Date of Effectiveness: 28 November 2024
Rev. No. | Date | Description of Revision |  | Author
1 | 2024-11-27 | Initial version |  | Julian Smith
Deployment Plan - Team Structure & General
Author | Andrea Fais
System Name | FlexNet Operations (FNO)
Devepolment team | Role | Person Name/Team | Site | Mail
| Deployment engineer | TBD
| Software Engineer | Julian Smith |  | julian.smith@revenera.com
| TPO | Julian Smith |  | julian.smith@revenera.com
| TPO - backup | Shalibh Singh |  | ShSingh@revenera.com
| R1, R2 SME | Brandy Porkarski |  | brandy.porkarski@materialise.com
| Solution Owner | Aylin Kertik |  | aylin.kertik@materialise.be
| Business Analyst SME | Mieke Roelens |  | mieke.roelens@materialise.be
| project manager | Andrea Fais |  | andrea.fais@materialise.be

## Environment&Dependencies
| Form F-ITOP-008 Deployment Plan |  | Revision Number: 01
Date of Effectiveness: 28 November 2024
Deployment Plan - Deployment environment & System Dependencies
Servers |  | PROD/UAT | Links to related Applications | Links accessible by External Applications
UAT | Application Server | https://flex13015-uat.flexnetoperations.eu/
PROD | Application Server | https://flex13015.flexnetoperations.eu/

## Deployment checklist
| Form F-ITOP-008 Deployment Plan | Revision Number: 01
Date of Effectiveness: 28 November 2024
Deployment Plan - Deployment checklist
Role | Actions | Comments
Deployment Prerequisites
Project manager | Inform all stakeholders about upcoming release | communicated and alignment scheduled for updates
TPO | provide access to deployment team to FNO | Oleksii Hrytsenko, Ihor Hut , Artem Kolomiichuk have access to UAT to compare the configurations in both environments.
Security | Open ports on FW
TPO | provide scripts to deployment team for site configuration, users, products and users import.
Deployment day
Release/Deploy Actions
| Deployment Instrcutions Document | link to deployment instructions
Deployment Engineer | Please follow the steps illustrated in the work instructions above
Additional steps
Testing
Solution Owner | Smoke testing for f/f functionalities
Deployment Finalization
Note on A4: Author: definition of who performs actions is under Release coordinator responsinilities; but roles can be predefined by Change Coordinator

## Acceptance checklist
| Form F-ITOP-008 Deployment Plan | Revision Number: 01
Date of Effectiveness: 28 November 2024
Deployment Plan - Acceptance criteria / Smoke test
Role | Condition / Acceptance criteria | Expected Result | Comments
Deployment engineer | Operational site is available to production users

## Rollback procedure
| Form F-ITOP-008 Deployment Plan | Revision Number: 01
Date of Effectiveness: 28 November 2024
Deployment Plan - Rollback procedure
Role | Actions | Comments
Rollback
Deployment Engineer | Rollback possible (manually) but not recommended, please contact Julian Smith or Shailabh Singh in this case, he will be in standy
Validation
Test engineer | Minimal smoke test passed with no exeptions

## Communication plan
| Form F-ITOP-008 Deployment Plan | Revision Number: 01
Date of Effectiveness: 28 November 2024
Deployment completed | Notification
| List of recipients | brandy.porkarski@materialise.com; "Tanvi Gulati" <tanvi.gulati@materialise.be>; "Aylin Kertik" <aylin.kertik@materialise.be>; "Alexander Furzeman" <Alexander.Furzeman@materialise.be>; "Julian Smith" <julian.smith@revenera.com>; "Yves Houtevels" <yves.houtevels@materialise.be>; "Ilse Marin" <ilse.marin@materialise.be>; "Alexander Tubolets" <Alexander.Tubolets@materialise.kiev.ua>; "Dmytro Balaba" <Dmytro.Balaba@materialise.kiev.ua>; "Yuliia Prokopenko" <yuliia.prokopenko@materialise.kiev.ua>; "Liliya Tovstenko" <Liliya.Tovstenko@materialise.kiev.ua>; "Sergii Iushchuk" <sergii.iushchuk@materialise.kiev.ua>; "Thien Eng Fu" <thieneng.fu@materialise.com.my>; "Olena Savenko" <olena.savenko@materialise.kiev.ua>; Guilherme Lopez" <Guilherme.Lopez@materialise.be>"Dmytro Balaba" <Dmytro.Balaba@materialise.kiev.ua>; "Sergii Iushchuk" <sergii.iushchuk@materialise.kiev.ua>; "Anna Voznyuk" <anna.voznyuk@materialise.kiev.ua>; "Andrii Iablokov" <andrii.iablokov@materialise.kiev.ua>; "Mieke Roelens" <mieke.roelens@materialise.be>; "Andrea Fais" <Andrea.Fais@materialise.be>; "Julian Smith" <julian.smith@revenera.com>; "Aylin Kertik" <aylin.kertik@materialise.be>
| Subject | Flex Flex Deployment Production Deployment MVP1
| Success message | Dear, I would like to inform you that the FNO release to Production has completed successfully. Regards,
| Failure message | Dear, I would like to inform you that the FNO release to UAT was not completed successfully. Regards,
Testing completed | List of recipients 2
List of recipients 1
| Subject | <iteration number>: release status/change number
| Success message | Dear Deployment team, I would like to inform you that smoke test passed successfully after release. No issues were discovered so far. Regards,
| Failure message 1 (roll-back needed) | Dear Deployment team, I would like to inform you that smoke test passed unsuccessfully after release. The roll-back plan should be implemented. Regards,
| Failure message 2 (roll-back not needed) | Dear Deployment team, I would like to inform you that smoke test passed with issues after release. We have found following issues ..., which didn't …entail rollback plan implementation . Regards,
Note on B15: Author: list of recipients: Deployment team
Note on B18: Author: List of recipients: Deployment team

## DATA
REV | Revision Number: 01
DOE | Date of Effectiveness: 28 November 2024
SOP | Form F-ITOP-008 Deployment Plan